## Overview
Book Management Web App — Development Plan
Stack | Backend: NestJS (MVC/Layered) ¦ DB: PostgreSQL + TypeORM ¦ Auth: JWT ¦ Frontend: TBD (React/Vue/Angular)
Goal | Web app to list, add, search, and delete books, with Book related to Author (many-to-many) and Category (one-to-many), plus JWT authentication protecting POST/DELETE on /api/books.
How to use this file
Give the 'Task List' sheet to your coding agent one phase at a time (or all at once). Update the Status column as work completes. 'API Reference' and 'ER Diagram Notes' are context sheets the agent should read before generating code.

## Task List
# | Phase | Task | Description / Agent Instructions | Priority | Status | Notes
1 | 0. Project Setup | Init NestJS project & dependencies | nest new book-management-api. Install @nestjs/typeorm, typeorm, pg, @nestjs/jwt, @nestjs/passport, passport-jwt, bcrypt, class-validator, class-transformer. | High | Not started
2 | 0. Project Setup | Configure environment & TypeORM | .env for DB credentials/JWT secret. TypeORM datasource config, synchronize=false, migrations folder configured. | High | Not started
3 | 0. Project Setup | Set up global validation & exception handling | ValidationPipe (whitelist, transform) in main.ts. Global exception filter for consistent 404/400 JSON error format. | Medium | Not started
4 | 1. Database | Create Author entity | id, name, bio. No direct FK (owned by join table). | High | Not started
5 | 1. Database | Create Category entity | id, name. | High | Not started
6 | 1. Database | Create Book entity | id, title, isbn, published_year, created_at, ManyToOne Category (category_id FK), ManyToMany Author via join table book_authors. | High | Not started
7 | 1. Database | Create User entity | id, username, password_hash, created_at. Used only for auth, no relation to Book/Author. | High | Not started
8 | 1. Database | Generate & run initial migration | typeorm migration:generate for all four tables + book_authors join table. Verify FKs match ER diagram. | High | Not started
9 | 1. Database | Seed sample data | Insert a handful of authors/categories/books/one test user so POST /api/books can reference real IDs during testing. | Medium | Not started
10 | 2. Backend — Authors/Categories | Authors module (Controller/Service) | GET /api/authors returns all authors, for frontend dropdown. | Medium | Not started
11 | 2. Backend — Authors/Categories | Categories module (Controller/Service) | GET /api/categories returns all categories, for frontend dropdown. | Medium | Not started
12 | 3. Backend — Books | Books module skeleton | Controller -> Service -> Repository layering. No direct DB calls in controller. | High | Not started
13 | 3. Backend — Books | GET /api/books | Return all books; support optional query filters ?categoryId= and/or ?authorId=. | High | Not started
14 | 3. Backend — Books | GET /api/books/:id | Return single book by id; 404 JSON if not found. | High | Not started
15 | 3. Backend — Books | POST /api/books | Create book; validate categoryId and authorId(s) exist before insert; return 201 with created record. | High | Not started
16 | 3. Backend — Books | DELETE /api/books/:id | Delete book by id; 204 on success, 404 if not found. | High | Not started
17 | 4. Backend — Auth | Users module | Store username + bcrypt-hashed password. | High | Not started
18 | 4. Backend — Auth | POST /api/login | Verify username/password, return JWT with expiry. | High | Not started
19 | 4. Backend — Auth | JwtStrategy + JwtAuthGuard | Validate Bearer token from Authorization header; reject with 401 if missing/invalid. | High | Not started
20 | 4. Backend — Auth | Protect POST/DELETE /api/books | Apply JwtAuthGuard only to POST and DELETE endpoints; GET stays public. | High | Not started
21 | 5. Backend — QA | Manual API test pass | Use Postman/Thunder Client: full flow login -> token -> POST/DELETE with & without token -> confirm 401/201/204/404 as specified. | Medium | Not started
22 | 5. Backend — QA | Export ER diagram / migration as design evidence | Keep schema.prisma-equivalent (TypeORM entities) or migration files + ER diagram image in repo. | Low | Not started
23 | 6. Frontend | Choose framework & scaffold | React/Vue/Angular — scaffold app, set up routing and base layout. | High | Not started
24 | 6. Frontend | Login page | Form posting to /api/login, store JWT (memory or secure storage), redirect on success. | High | Not started
25 | 6. Frontend | Book list page | Fetch GET /api/books, render table/list, filter dropdowns fed by GET /api/authors and GET /api/categories. | High | Not started
26 | 6. Frontend | Add book form | Dropdowns for category/author(s), POST to /api/books with Bearer token, show validation errors. | High | Not started
27 | 6. Frontend | Delete book action | Confirm dialog, DELETE /api/books/:id with Bearer token, refresh list. | High | Not started
28 | 6. Frontend | Auth guard on frontend routes | Redirect to login if no valid token before allowing add/delete actions. | Medium | Not started
29 | 7. Polish | Error & loading states | Handle 401 (redirect to login), 404, network errors gracefully across pages. | Low | Not started
30 | 7. Polish | README | Setup instructions, .env example, how to run migrations/seed, API summary. | Low | Not started

## API Reference
Method | Endpoint | Auth required | Success | Error | Notes
GET | /api/books | No | 200 | - | Optional query: ?categoryId=&authorId=
GET | /api/books/:id | No | 200 | 404 if not found
POST | /api/books | Yes (Bearer JWT) | 201 + created book | 401 if no/invalid token; 400 if categoryId/authorId(s) don't exist
DELETE | /api/books/:id | Yes (Bearer JWT) | 204 | 401 if no/invalid token; 404 if not found
GET | /api/authors | No | 200 | - | For frontend dropdown
GET | /api/categories | No | 200 | - | For frontend dropdown
POST | /api/login | No | 200 + JWT | 401 on bad credentials | JWT should have an expiry set

## ER Diagram Notes
Table | Key fields | Relationship
USER | id (PK), username, password_hash, created_at | No relation to other tables — auth only.
CATEGORY | id (PK), name | 1 — N with BOOK (one category has many books).
AUTHOR | id (PK), name, bio | N — N with BOOK via BOOK_AUTHORS.
BOOK | id (PK), title, isbn, published_year, category_id (FK), created_at | N — 1 with CATEGORY; N — N with AUTHOR via BOOK_AUTHORS.
BOOK_AUTHORS | book_id (FK), author_id (FK) | Join table resolving BOOK <-> AUTHOR many-to-many.